# Part 7

# options

If all your core team’s activities (design, art, programming) have an overrun of 0 or fewer weeks, you can skip all this.

If one or more of your teams has a positive overrun, you need to decide on a course of action. This can be at a company-wide level (eg. try to negotiate an extension), at a team level (eg. hire more programmers) or a combination (eg. try to negotiate an extension and hire more programmers).

You can choose no more than one company-wide option, but are allowed as many options from team-specific each set as you desire (so long as any preconditions are met).

Note: some of the options described here may actually make matters worse…

#### Company-wide Options

The company-wide options affect all your teams equally. There are two of them:

- Negotiate an extension. Marketing Director Lauren Warren is confident she can do this, but is apprehensive because of the effect on sales and the company’s reputation.

- Negotiate an extension for the Xbox One X version only. Launch the PC version on time regardless of its quality. Hold back on the Xbox version until it’s complete, citing production problems (blame previous management). Produce a patch to the PC version when the Xbox version is finally launched.

There’s no option to hold back on the PC version and launch a buggy Xbox version because Quadrant Q would never pass the quality control requirements for certification if it were buggy.

#### Team-specific Options

The team-specific options affect only the team concerned.

## Design team options

- Hire extra designers.

- If one of your teams has no overrun, get its members to pitch in with design.

- If you have an assistant whom you didn’t promote in part 4, pitch in with the design yourself.

- Launch with an incomplete design. Have Lauren Warren announce that the apparently incomplete parts are for later DLC.

- Firefight, so that although the product is incomplete it can launch in a coherent form.

- Crack the whip and ask the designers to work evenings and weekends to get it finished on time.

## Programmer team options

- Hire extra programmers.

- If your design team has no overrun, redesign to remove some unimplemented functionality.

- If you promoted Michaela Taylor to CTO or Giles Stiles is your Lead Programmer and you didn’t interfere in part 4 or if  Norman Foreman is your Lead Programmer and you sided with Michaela in part 4, persuade COO Michaela Taylor to undertake some of the more onerous administrative tasks that require technical know-how but not domain-specific knowledge, eg. system integration. Michaela is happy to help, because of your earlier support.

- Launch without proper testing. Remove the show-stopper bugs and catch the rest post-launch.

- If your Lead Programmer is not Sandra Nandhra, crack the whip and ask the programmers to work evenings and weekends to get it finished on time. Sandra made it abundantly clear that she doesn’t like crunch and will have no truck with it.

## Art team options

- Hire extra artists.

- If your design team has no overrun and you’re not making them redesign, redesign to remove some unimplemented graphics.

- Try to get help from Gemu Gemu Gemu. They have other development studios, and those studios have artists.

- Launch with a substandard artwork in places. Re-use art that wasn’t supposed to be re-used, buy in textures from external sources, don’t polish the animation so much. You can always patch it later.

- If your programming team has no overrun, code tools to generate textures procedurally.

- Crack the whip and ask the artists to work evenings and weekends to get it finished on time.